## Sheet1
People | Assignment Type | Client | Project / Holiday | Position | Business Unit | Total Availability | Assignment Status | BU/Pôle | W06 - Feb 03 | W07 - Feb 10 | W08 - Feb 17 | W09 - Feb 24 | W10 - Mar 03 | W11 - Mar 10 | W12 - Mar 17 | W13 - Mar 24 | W14 - Mar 31 | W15 - Apr 07 | W16 - Apr 14 | W17 - Apr 21 | W18 - Apr 28
FZ | Real | T3 | T3 | Junior 1 | AUDIT | 2 |  | Audit MHZ | [10 empty] | 20%
FZ | Real | T1 | T1 | Junior 1 | AUDIT | 2 |  | Audit MHZ | [5 empty] | 100% | 100% | 60% | 100% | 100%
FZ | Real | T2 | T2 | Junior 1 | AUDIT | 2 |  | Audit MHZ | 100% | 100% | 100% | 100% | 100% | [5 empty] | 80% | 100% | 100%
KWG | Real | MKWG1 | MKWG1 | Junior 1 | AUDIT | 2 |  | Audit IL | 80% | 100%
KWG | Real | MKWG2 | MKWG2 | Junior 1 | AUDIT | 2 |  | Audit IL | [7 empty] | 60%
KWG | Real | MKWG3 | MKWG3 | Junior 1 | AUDIT | 2 |  | Audit IL | [11 empty] | 60% | 100%
KWG | Real | MKWG4 | MKWG4 | Junior 1 | AUDIT | 2 |  | Audit IL | [9 empty] | 20%
KWG | Real | MKWG5 | MKWG5 | Junior 1 | AUDIT | 2 |  | Audit IL | 20% | [7 empty] | 60% | 80% | 100% | 40%
KWG | Real | MKWG6 | MKWG6 | Junior 1 | AUDIT | 2 |  | Audit IL |  |  |  |  | 60% | 100% | 60% | 20%
KWG | Real | MKWG7 | MKWG7 | Junior 1 | AUDIT | 2 |  | Audit IL |  |  | 100% |  |  |  | 40% | 20%
KWG | Real | MKWG8 | MKWG8 | Junior 1 | AUDIT | 2 |  | Audit IL |  |  |  | 100% | 40%
NID | Real | MNID1 | MNID1 | Senior 1 | AUDIT | 28 |  | Audit IL | [5 empty] | 100%
NID | Real | MNID2 | MNID2 | Senior 1 | AUDIT | 28 |  | Audit IL | 100%
NID | Real | MNID3 | MNID3 | Senior 1 | AUDIT | 28 |  | Audit IL |  | 100% | 100% | 100% | 100%
NID | Real | MNID4 | MNID4 | Senior 1 | AUDIT | 28 |  | Audit IL | [6 empty] | 100%
MT | Real | MMT1 | MMT1 | Junior 2 | AUDIT | 53 |  | Audit ERK | 100% | 100%
IT | Real | MIT1 | MIT1 | Senior 2 | AUDIT | 2 |  | Audit SM | [7 empty] | 100% | 60% | 100% | 100% | 100% | 100%
IT | Real | MIT2 | MIT2 | Senior 2 | AUDIT | 2 |  | Audit SM | 100%
IT | Real | MIT3 | MIT3 | Senior 2 | AUDIT | 2 |  | Audit SM | [5 empty] | 100% | 100%
IT | Real | MIT4 | MIT4 | Senior 2 | AUDIT | 2 |  | Audit SM |  | 100% | 100% | 100% | 100%
DT | Real | DT1 | DT1 | Junior 1 | AUDIT | 3 |  | Audit KB | [8 empty] | 100% | 100%
DT | Real | DT2 | DT2 | Junior 1 | AUDIT | 3 |  | Audit KB | [6 empty] | 100% | 100%
DT | Real | DT3 | DT3 | Junior 1 | AUDIT | 3 |  | Audit KB | [10 empty] | 100% | 100%
DT | Real | DT4 | DT4 | Junior 1 | AUDIT | 3 |  | Audit KB |  |  | 100% | 100% | 100% | 100%
DT | Real | DT5 | DT5 | Junior 1 | AUDIT | 3 |  | Audit KB | 100% | 100%
MTZ | Real | MMTZ1 | MMTZ1 | Manager 1 | AUDIT | 53 |  | Audit SM | 100% | 100%
AT | Real | MAT1 | MAT1 | Senior 1 | AUDIT | 5 |  | Audit KB |  |  |  |  | 100% | 100%
AT | Real | MAT2 | MAT2 | Senior 1 | AUDIT | 5 |  | Audit KB |  | 100% | 100% | 100% | [5 empty] | 100% | 100%
AT | Real | MAT2 | MAT2 | Senior 1 | AUDIT | 5 |  | Audit KB | [12 empty] | 100%
AT | Real | MAT2 | MAT2 | Senior 1 | AUDIT | 5 |  | Audit KB | [11 empty] | 100%
AT | Real | MAT2 | MAT2 | Senior 1 | AUDIT | 5 |  | Audit KB | [6 empty] | 100% | 100% | 100%
AT | Real | MAT2 | MAT2 | Senior 1 | AUDIT | 5 |  | Audit KB |  |  |  |  | 100%
MTA | Real | MMTA1 | MMTA1 | Senior 2 | AUDIT | 2 |  | Audit SM |  |  |  |  | 100% | 100%
MTA | Real | MMTA2 | MMTA2 | Senior 2 | AUDIT | 2 |  | Audit SM | [11 empty] | 100% | 100%
MTA | Real | MMTA3 | MMTA3 | Senior 2 | AUDIT | 2 |  | Audit SM | [7 empty] | 100% | 60% | 100% | 100% | 100%
MTA | Real | MMTA4 | MMTA4 | Senior 2 | AUDIT | 2 |  | Audit SM | 100% | 100%
MTA | Real | MMTA5 | MMTA5 | Senior 2 | AUDIT | 2 |  | Audit SM |  |  | 100% | 100% |  |  | 100%
ASR | Real | MASR1 | MASR1 | Senior 1 | AUDIT | 8 |  | Audit IL | [7 empty] | 60% | 100% | 80%
ASR | Real | MASR2 | MASR2 | Senior 1 | AUDIT | 8 |  | Audit IL | [10 empty] | 100% | 100% | 100%
ASR | Real | MASR3 | MASR3 | Senior 1 | AUDIT | 8 |  | Audit IL |  |  |  |  | 100% | 100% | 100%
ASR | Real | MASR4 | MASR4 | Senior 1 | AUDIT | 8 |  | Audit IL | 100% | 100% | 100%
SMA | Real | MSMA1 | MSMA1 | Manager 3 | AUDIT | 33.33 |  | Audit SM | 33% | 33% | 27%
SMA | Real | MSMA2 | MSMA2 | Manager 3 | AUDIT | 33.33 |  | Audit SM | 100% |  |  |  | 100% | 100%
SMA | Real | MSMA3 | MSMA3 | Manager 3 | AUDIT | 33.33 |  | Audit SM |  | 36% | 36% | 29% | 50%
SMA | Real | MSMA4 | MSMA4 | Manager 3 | AUDIT | 33.33 |  | Audit SM |  | 33% | 33% | 33% | 50%
SMA | Real | MSMA5 | MSMA5 | Manager 3 | AUDIT | 33.33 |  | Audit SM |  |  |  |  | 40%
SMA | Real | MSMA6 | MSMA6 | Manager 3 | AUDIT | 33.33 |  | Audit SM |  | 33% | 33% | 33% | 75%
HRS | Real | MHRS1 | MHRS1 | Junior 1 | AUDIT | 22.8 |  | Audit ERK |  | 50% | 90% | 90% | 90% | 90% | 90% | 90% | 18%
HRS | Real | MHRS2 | MHRS2 | Junior 1 | AUDIT | 22.8 |  | Audit ERK | 90% | 20%
HRS | Real | MHRS3 | MHRS3 | Junior 1 | AUDIT | 22.8 |  | Audit ERK |  | 20%
HRS | Real | MHRS4 | MHRS4 | Junior 1 | AUDIT | 22.8 |  | Audit ERK | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 2%
HS | Real | MHS1 | MHS1 | Senior 3 | AUDIT | 23.6 |  | Audit ERK | 80%
HS | Real | MHS2 | MHS2 | Senior 3 | AUDIT | 23.6 |  | Audit ERK |  | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 20%
HS | Real | MHS3 | MHS3 | Senior 3 | AUDIT | 23.6 |  | Audit ERK | 20% | 20%
HS | Real | MHS4 | MHS4 | Senior 3 | AUDIT | 23.6 |  | Audit ERK |  | 20%
LS | Real | MLS1 | MLS1 | Junior 2 | AUDIT | 23 |  | Audit ERK | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
EKS | Real | MKES1 | MKES1 | Junior 1 | AUDIT | 10 |  | Audit SM |  |  |  |  | 100% | 100%
EKS | Real | MKES2 | MKES2 | Junior 1 | AUDIT | 10 |  | Audit SM | [7 empty] | 20% | 20%
EKS | Real | MKES3 | MKES3 | Junior 1 | AUDIT | 10 |  | Audit SM | [6 empty] | 100% | 80% | 40% | 60%
EKS | Real | MKES4 | MKES4 | Junior 1 | AUDIT | 10 |  | Audit SM | [11 empty] | 100% | 100%
EKS | Real | MKES5 | MKES5 | Junior 1 | AUDIT | 10 |  | Audit SM |  | 100%
EKS | Real | MKES6 | MKES6 | Junior 1 | AUDIT | 10 |  | Audit SM |  |  | 80% | 100%
EKS | Real | MKES7 | MKES7 | Junior 1 | AUDIT | 10 |  | Audit SM | 100%
RSA | Real | MRSA1 | MRSA1 | Senior 1 | AUDIT | 0 |  | Audit SM | [10 empty] | 20%
RSA | Real | MRSA2 | MRSA2 | Senior 1 | AUDIT | 0 |  | Audit SM | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 80% | 100% | 100%
SSY | Real | SSY1 | SSY1 | Director 1 | AUDIT | 14 |  | Audit MHZ |  |  |  |  | 60% | 60% | 60% | 60% | 20%
SSY | Real | SSY2 | SSY2 | Director 1 | AUDIT | 14 |  | Audit MHZ | 60% | 60% | 60% | 60% | 40% | 40% | 20% |  | 40% | 80% | 100% | 100% | 100%
MS | Real | MMS1 | MMS1 | Senior 3 | AUDIT | 6 |  | Audit IL | [7 empty] | 40% | 100% | 80% | 60%
MS | Real | MMS2 | MMS2 | Senior 3 | AUDIT | 6 |  | Audit IL | [10 empty] | 20% | 100% | 100%
MS | Real | MMS3 | MMS3 | Senior 3 | AUDIT | 6 |  | Audit IL | 100% | 100% | 80%
MS | Real | MMS4 | MMS4 | Senior 3 | AUDIT | 6 |  | Audit IL |  |  |  | 100% | 100% | 100% | 100%
RIB | Real | MRIB1 | MRIB1 | Junior 1 | AUDIT | 12 |  | Audit IL | [7 empty] | 40% | 100% | 80% | 60%
RIB | Real | MRIB2 | MRIB2 | Junior 1 | AUDIT | 12 |  | Audit IL | [10 empty] | 40%
RIB | Real | MRIB3 | MRIB3 | Junior 1 | AUDIT | 12 |  | Audit IL | [6 empty] | 100%
RIB | Real | MRIB4 | MRIB4 | Junior 1 | AUDIT | 12 |  | Audit IL | 100% | 100% | 100%
RIB | Simulated | MRIB5 | MRIB5 | Junior 1 | AUDIT | 12 |  | Audit IL |  |  |  | 100% | 100% | 100%
ARZ | Real | MARZ1 | MARZ1 | Junior 2 | AUDIT | 2 |  | Audit SM |  |  |  |  | 40% | 100%
ARZ | Real | MARZ2 | MARZ2 | Junior 2 | AUDIT | 2 |  | Audit SM | 100% | [11 empty] | 100%
ARZ | Real | MARZ3 | MARZ3 | Junior 2 | AUDIT | 2 |  | Audit SM | [6 empty] | 80%
ARZ | Real | MARZ4 | MARZ4 | Junior 2 | AUDIT | 2 |  | Audit SM | [6 empty] | 20%
ARZ | Real | MARZ5 | MARZ5 | Junior 2 | AUDIT | 2 |  | Audit SM | [11 empty] | 100% | 100%
ARZ | Real | MARZ6 | MARZ6 | Junior 2 | AUDIT | 2 |  | Audit SM | [7 empty] | 100% | 60% | 100% | 100% | 100% | 100%
ARZ | Real | MARZ7 | MARZ7 | Junior 2 | AUDIT | 2 |  | Audit SM |  | 100% | 100% | 100% | 60%
AR | Real | MARK1 | MARK1 | Junior 2 | AUDIT | 5 |  | Audit MHZ | 60%
AR | Real | MARK2 | MARK2 | Junior 2 | AUDIT | 5 |  | Audit MHZ |  |  |  | 100% | 100%
AR | Real | MARK3 | MARK3 | Junior 2 | AUDIT | 5 |  | Audit MHZ | 40% | 100%
AR | Real | MARK4 | MARK4 | Junior 2 | AUDIT | 5 |  | Audit MHZ |  |  | 100%
AR | Real | MARK5 | MARK5 | Junior 2 | AUDIT | 5 |  | Audit MHZ | [9 empty] | 100%
AR | Real | MARK6 | MARK6 | Junior 2 | AUDIT | 5 |  | Audit MHZ | [5 empty] | 100% | 100% | 100%
AR | Real | MARK7 | MARK7 | Junior 2 | AUDIT | 5 |  | Audit MHZ | [10 empty] | 100% | 100% | 100%
ER | Real | MER1 | MER1 | Partner | AUDIT | 29.1 |  | Audit ERK | 5%
ER | Real | MER2 | MER2 | Partner | AUDIT | 29.1 |  | Audit ERK |  | 80% | 85% |  | 80% | 80% |  | 80% | 16%
ER | Real | MER3 | MER3 | Partner | AUDIT | 29.1 |  | Audit ERK | 40% |  |  |  | 20% |  | 70%
ER | Real | MER4 | MER4 | Partner | AUDIT | 29.1 |  | Audit ERK | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 2%
ER | Real | MER5 | MER5 | Partner | AUDIT | 29.1 |  | Audit ERK | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 2%
ER | Real | MER6 | MER6 | Partner | AUDIT | 29.1 |  | Audit ERK |  |  |  | 20%
MO | Real | MMO1 | MMO1 | Senior 1 | AUDIT | 30 |  | Audit IL |  | 60% | 100% | 100% | 100% | 100%
MO | Real | MMO2 | MMO2 | Senior 1 | AUDIT | 30 |  | Audit IL | [8 empty] | 20% | 20%
MO | Real | MMO3 | MMO3 | Senior 1 | AUDIT | 30 |  | Audit IL | [8 empty] | 80%
MO | Real | MMO4 | MMO4 | Senior 1 | AUDIT | 30 |  | Audit IL | [7 empty] | 80%
AO | Real | MAO1 | MAO1 | Junior 1 | AUDIT | 22.8 |  | Audit ERK |  | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 20%
AO | Real | MAO2 | MAO2 | Junior 1 | AUDIT | 22.8 |  | Audit ERK | 100% | 20%
AO | Real | MAO3 | MAO3 | Junior 1 | AUDIT | 22.8 |  | Audit ERK |  | 20%
OHT | Real | MOHT1 | MOHT1 | Junior 1 | AUDIT | 9 |  | Audit SM | 100% | 100%
OHT | Real | MOHT2 | MOHT2 | Junior 1 | AUDIT | 9 |  | Audit SM |  |  |  | 60% | 50%
OHT | Real | MOHT3 | MOHT3 | Junior 1 | AUDIT | 9 |  | Audit SM |  |  |  |  | 50% | 100%
OHT | Real | MOHT4 | MOHT4 | Junior 1 | AUDIT | 9 |  | Audit SM | [6 empty] | 20%
OHT | Real | MOHT5 | MOHT5 | Junior 1 | AUDIT | 9 |  | Audit SM | [7 empty] | 100% |  | 100% | 100% | 100% | 100%
OHT | Real | MOHT6 | MOHT6 | Junior 1 | AUDIT | 9 |  | Audit SM |  |  | 100% | 40%
OHT | Real | MOHT7 | MOHT7 | Junior 1 | AUDIT | 9 |  | Audit SM | [12 empty] | 100%
MAO | Real | MAO1 | MAO1 | Junior 1 | AUDIT | 10 |  | Audit IL | 100% | 100% | 100% | 100% | 100% | 100% | 100%
MAO | Real | MAO2 | MAO2 | Junior 1 | AUDIT | 10 |  | Audit IL | [9 empty] | 100% | 100% | 100% | 100%
JN | Real | MJN1 | MJN1 | Senior 1 | AUDIT | 2 |  | Audit SM | 50% | 50%
JN | Real | MJN2 | MJN2 | Senior 1 | AUDIT | 2 |  | Audit SM | 50% | 50%
JN | Real | MJN3 | MJN3 | Senior 1 | AUDIT | 2 |  | Audit SM |  |  |  |  | 100% | 100% | 100% | 100%
JN | Real | MJN4 | MJN4 | Senior 1 | AUDIT | 2 |  | Audit SM | [8 empty] | 60% | 100% | 100% | 100% | 100%
JN | Real | MJN5 | MJN5 | Senior 1 | AUDIT | 2 |  | Audit SM |  |  | 100% | 100%
NEN | Real | NEN1 | NEN1 | Senior 3 | AUDIT | 2 |  | Audit MHZ | [5 empty] | 100% | 100% | 100% | 60% | 100% | 100%
NEN | Real | NEN2 | NEN2 | Senior 3 | AUDIT | 2 |  | Audit MHZ | [11 empty] | 100% | 100%
NEN | Real | NEN3 | NEN3 | Senior 3 | AUDIT | 2 |  | Audit MHZ |  | 100% | 100% | 100% | 100%
NEN | Real | NEN4 | NEN4 | Senior 3 | AUDIT | 2 |  | Audit MHZ | 100%
MNJ | Real | MMNJ1 | MMNJ1 | Junior 2 | AUDIT | 2 |  | Audit MHZ |  |  |  | 100%
MNJ | Real | MMNJ2 | MMNJ2 | Junior 2 | AUDIT | 2 |  | Audit MHZ | 100% | 100% | 100% |  | 100% | 100%
MNJ | Real | MMNJ3 | MMNJ3 | Junior 2 | AUDIT | 2 |  | Audit MHZ | [10 empty] | 80% | 100% | 100%
MNJ | Real | MMNJ4 | MMNJ4 | Junior 2 | AUDIT | 2 |  | Audit MHZ | [6 empty] | 100% | 100% | 60% | 100% | 20%
MMZ | Real | MMMZ1 | MMMZ1 | Junior 1 | AUDIT | 15 |  | Audit SM | 100% | 100%
MMZ | Real | MMMZ2 | MMMZ2 | Junior 1 | AUDIT | 15 |  | Audit SM | [8 empty] | 60%
MMZ | Real | MMMZ3 | MMMZ3 | Junior 1 | AUDIT | 15 |  | Audit SM | [6 empty] | 80% | 100%
MMZ | Real | MMMZ4 | MMMZ4 | Junior 1 | AUDIT | 15 |  | Audit SM |  |  | 100% | 100%
MMZ | Real | MMMZ5 | MMMZ5 | Junior 1 | AUDIT | 15 |  | Audit SM | [11 empty] | 80%
MMZ | Real | MMMZ6 | MMMZ6 | Junior 1 | AUDIT | 15 |  | Audit SM | [11 empty] | 20%
MMZ | Real | MMMZ7 | MMMZ7 | Junior 1 | AUDIT | 15 |  | Audit SM |  |  |  |  | 100% | 100% | 20%
PLM | Real | MPLM1 | MPLM1 | Junior 1 | AUDIT | 4 |  | Audit MAB | [7 empty] | 20%
PLM | Real | MPLM2 | MPLM2 | Junior 1 | AUDIT | 4 |  | Audit MAB | 20% |  | 60% | 80%
PLM | Real | MPLM3 | MPLM3 | Junior 1 | AUDIT | 4 |  | Audit MAB | 20% | 60% |  |  | 100% | 100% | 80% | 20%
PLM | Real | MPLM4 | MPLM4 | Junior 1 | AUDIT | 4 |  | Audit MAB | [10 empty] | 100% | 100% | 100%
PLM | Real | MPLM5 | MPLM5 | Junior 1 | AUDIT | 4 |  | Audit MAB | [9 empty] | 80%
PLM | Real | MPLM6 | MPLM6 | Junior 1 | AUDIT | 4 |  | Audit MAB | 20% | 20% | 20% | 20% |  |  |  | 60%
PLM | Real | MPLM7 | MPLM7 | Junior 1 | AUDIT | 4 |  | Audit MAB | 40% | 20% | 20% | [5 empty] | 60%
RLI | Real | MRLI1 | MRLI1 | Junior 2 | AUDIT | 2 |  | Audit SM |  |  |  |  | 100% | 100% | 100%
RLI | Real | MRLI2 | MRLI2 | Junior 2 | AUDIT | 2 |  | Audit SM | [8 empty] | 20%
RLI | Real | MRLI3 | MRLI3 | Junior 2 | AUDIT | 2 |  | Audit SM | [11 empty] | 100% | 100%
RLI | Real | MRLI4 | MRLI4 | Junior 2 | AUDIT | 2 |  | Audit SM | [10 empty] | 100%
RLI | Real | MRLI5 | MRLI5 | Junior 2 | AUDIT | 2 |  | Audit SM | [7 empty] | 100% | 40% | 100%
RLI | Real | MRLI6 | MRLI6 | Junior 2 | AUDIT | 2 |  | Audit SM | 100% | 100%
RLI | Real | MRLI7 | MRLI7 | Junior 2 | AUDIT | 2 |  | Audit SM |  |  | 100% | 100%
HM | Real | MHM1 | MHM1 | Senior 2 | AUDIT | 33 |  | Audit ERK | 83% | 75% | 75% | 75% | 100% | 100%
HM | Real | MHM2 | MHM2 | Senior 2 | AUDIT | 33 |  | Audit ERK | 25% | 25% | 25% | 25%
CM | Real | MCM1 | MCM1 | Senior 2 | AUDIT | 0 |  | Audit IL | [5 empty] | 100% | 100% | 100% |  |  | 100% | 40% | 100%
CM | Real | MCM2 | MCM2 | Senior 2 | AUDIT | 0 |  | Audit IL | [8 empty] | 100% | 100% |  | 60%
CM | Real | MCM3 | MCM3 | Senior 2 | AUDIT | 0 |  | Audit IL | 100% | 100% | 100% | 100% | 100%
CM | Real | MCM4 | MCM4 | Senior 2 | AUDIT | 0 |  | Audit IL |  |  | 100%
MHM | Real | MMHM1 | MMHM1 | Senior 2 | AUDIT | 2 |  | Audit MHZ |  |  | 100% | 100%
MHM | Real | MMHM2 | MMHM2 | Senior 2 | AUDIT | 2 |  | Audit MHZ |  | 80%
MHM | Real | MMHM3 | MMHM3 | Senior 2 | AUDIT | 2 |  | Audit MHZ | [7 empty] | 100% | 60%
MHM | Real | MMHM4 | MMHM4 | Senior 2 | AUDIT | 2 |  | Audit MHZ |  |  |  |  | 100% | 100% | 100%
MHM | Real | MMHM5 | MMHM5 | Senior 2 | AUDIT | 2 |  | Audit MHZ | [9 empty] | 100%
MHM | Real | MMHM6 | MMHM6 | Senior 2 | AUDIT | 2 |  | Audit MHZ | 100% | 20%
MHM | Real | MMHM7 | MMHM7 | Senior 2 | AUDIT | 2 |  | Audit MHZ | [10 empty] | 100% | 100% | 100%
MLP | Real | MMLP001 | MMLP001 | Partner | AUDIT | 8.63 |  | Audit IL | [9 empty] | 10% | 10%
MLP | Real | MMLP002 | MMLP002 | Partner | AUDIT | 8.63 |  | Audit IL | [12 empty] | 33%
MLP | Real | MMLP003 | MMLP003 | Partner | AUDIT | 8.63 |  | Audit IL | 10% | 10% | 10% | 10% | 10% | 10% | 10%
MLP | Real | MMLP004 | MMLP004 | Partner | AUDIT | 8.63 |  | Audit IL | [7 empty] | 10% |  |  | 10%
MLP | Real | MMLP005 | MMLP005 | Partner | AUDIT | 8.63 |  | Audit IL | [8 empty] | 10%
MLP | Real | MMLP006 | MMLP006 | Partner | AUDIT | 8.63 |  | Audit IL | [8 empty] | 10%
MLP | Real | MMLP007 | MMLP007 | Partner | AUDIT | 8.63 |  | Audit IL | [9 empty] | 6%
MLP | Real | MMLP008 | MMLP008 | Partner | AUDIT | 8.63 |  | Audit IL |  |  |  |  | 20% |  | 10% | 10%
MLP | Real | MMLP009 | MMLP009 | Partner | AUDIT | 8.63 |  | Audit IL | [5 empty] | 20%
MLP | Real | MMLP0010 | MMLP0010 | Partner | AUDIT | 8.63 |  | Audit IL | [10 empty] | 10% | 15%
MLP | Real | MMLP0011 | MMLP0011 | Partner | AUDIT | 8.63 |  | Audit IL | [10 empty] | 10% | 10% | 17%
MLP | Real | MMLP0012 | MMLP0012 | Partner | AUDIT | 8.63 |  | Audit IL | [9 empty] | 3%
MLP | Real | MMLP0013 | MMLP0013 | Partner | AUDIT | 8.63 |  | Audit IL |  | 5%
MLP | Real | MMLP0014 | MMLP0014 | Partner | AUDIT | 8.63 |  | Audit IL | [5 empty] | 10%
MLP | Real | MMLP0015 | MMLP0015 | Partner | AUDIT | 8.63 |  | Audit IL | [9 empty] | 10% | 10%
MLP | Real | MMLP0016 | MMLP0016 | Partner | AUDIT | 8.63 |  | Audit IL |  | 10% | 10% | 20% | 10% |  | 20%
MLP | Real | MMLP0017 | MMLP0017 | Partner | AUDIT | 8.63 |  | Audit IL | [6 empty] | 10% |  | 10%
MLP | Real | MMLP0018 | MMLP0018 | Partner | AUDIT | 8.63 |  | Audit IL |  |  | 10% |  |  |  |  | 10% |  |  | 10% | 20%
MLP | Real | MMLP0019 | MMLP0019 | Partner | AUDIT | 8.63 |  | Audit IL |  | 10% |  |  |  | 20% |  | 10% |  | 10% | 20% | 10% | 17%
MLP | Real | MMLP0020 | MMLP0020 | Partner | AUDIT | 8.63 |  | Audit IL | 50% | 30% |  | 10% | 10% | 30% | 30% | 50% | 10% | 20% | 20% | 40% | 33%
MLP | Real | MMLP0021 | MMLP0021 | Partner | AUDIT | 8.63 |  | Audit IL |  |  | 3%
MLP | Real | MMLP0022 | MMLP0022 | Partner | AUDIT | 8.63 |  | Audit IL | 20% | 20% | 20% | 20%
MLP | Real | MMLP0023 | MMLP0023 | Partner | AUDIT | 8.63 |  | Audit IL |  |  | 15%
MLP | Real | MMLP0024 | MMLP0024 | Partner | AUDIT | 8.63 |  | Audit IL |  |  |  |  | 10% |  | 10%
MLP | Real | MMLP0025 | MMLP0025 | Partner | AUDIT | 8.63 |  | Audit IL |  |  |  | 15%
MLP | Real | MMLP0026 | MMLP0026 | Partner | AUDIT | 8.63 |  | Audit IL | [8 empty] | 1%
MLP | Real | MMLP0027 | MMLP0027 | Partner | AUDIT | 8.63 |  | Audit IL | [8 empty] | 3%
MLP | Real | MMLP0028 | MMLP0028 | Partner | AUDIT | 8.63 |  | Audit IL | [7 empty] | 3%
MLP | Real | MMLP0029 | MMLP0029 | Partner | AUDIT | 8.63 |  | Audit IL |  |  |  | 15%
MLP | Real | MMLP0030 | MMLP0030 | Partner | AUDIT | 8.63 |  | Audit IL |  |  |  |  | 10%
MLP | Real | MMLP0031 | MMLP0031 | Partner | AUDIT | 8.63 |  | Audit IL |  |  | 10%
MLP | Real | MMLP0032 | MMLP0032 | Partner | AUDIT | 8.63 |  | Audit IL |  | 10%
MLP | Real | MMLP0033 | MMLP0033 | Partner | AUDIT | 8.63 |  | Audit IL | 20%
MLP | Real | MMLP0034 | MMLP0034 | Partner | AUDIT | 8.63 |  | Audit IL | [5 empty] | 10%
MLP | Real | MMLP0035 | MMLP0035 | Partner | AUDIT | 8.63 |  | Audit IL |  |  |  |  | 15%
IL | Real | IL1 | IL1 | Junior 2 | AUDIT | 19 |  | Audit IL | 100% | 100% | 100% | 100% | 100% | 80% | 100%
IL | Real | IL2 | IL2 | Junior 2 | AUDIT | 19 |  | Audit IL | [10 empty] | 100% | 100%
MKT | Real | MMKT1 | MMKT1 | Junior 1 | AUDIT | 30 |  | Audit KB |  |  |  |  | 60% |  | 100%
MKT | Real | MMKT2 | MMKT2 | Junior 1 | AUDIT | 30 |  | Audit KB |  | 100% | 100% | 100% |  | 100%
MKT | Real | MMKT3 | MMKT3 | Junior 1 | AUDIT | 30 |  | Audit KB | 100%
NEP | Real | MNEP1 | MNEP1 | Manager 3 | AUDIT | 28 |  | Audit SM |  |  |  |  | 100%
NEP | Real | MNEP2 | MNEP2 | Manager 3 | AUDIT | 28 |  | Audit SM | [5 empty] | 100% | 100%
NEP | Real | MNEP3 | MNEP3 | Manager 3 | AUDIT | 28 |  | Audit SM | [7 empty] | 100%
NEP | Real | MNEP4 | MNEP4 | Manager 3 | AUDIT | 28 |  | Audit SM | 100% |  | 100% | 100%
AK | Real | MAK1 | MAK1 | Senior 2 | AUDIT | 8 |  | Audit SM | 100% | 100% | [7 empty] | 100%
AK | Real | MAK2 | MAK2 | Senior 2 | AUDIT | 8 |  | Audit SM |  |  |  |  | 100% | 100% | 100% | 100% | 100%
AK | Real | MAK3 | MAK3 | Senior 2 | AUDIT | 8 |  | Audit SM |  | 100% | 100% | 100%
AK | Real | MAK4 | MAK4 | Senior 2 | AUDIT | 8 |  | Audit SM | [10 empty] | 100%
MDK | Real | MMDK1 | MMDK1 | Senior 2 | AUDIT | 2 |  | Audit MHZ |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 60% | 100% | 100% | 100%
MDK | Real | MMDK2 | MMDK2 | Senior 2 | AUDIT | 2 |  | Audit MHZ | [12 empty] | 100%
MDK | Real | MMDK3 | MMDK3 | Senior 2 | AUDIT | 2 |  | Audit MHZ | 100%
FJ | Real | MFJ1 | MFJ1 | Senior 3 | AUDIT | 1 |  | Audit KB | [6 empty] | 100% | 100% | 80% | 100% | 100% | 100% | 100%
FJ | Real | MFJ2 | MFJ2 | Senior 3 | AUDIT | 1 |  | Audit KB | 100% | 100%
FJ | Real | MFJ3 | MFJ3 | Senior 3 | AUDIT | 1 |  | Audit KB |  |  | 100% | 100% | 100% | 100%
NJI | Real | MNJI1 | MNJI1 | Senior 3 | AUDIT | 18 |  | Audit IL | [11 empty] | 80% | 100%
NJI | Real | MNJI2 | MNJI2 | Senior 3 | AUDIT | 18 |  | Audit IL | 100% | 100% | 100% | 100% | 100%
NJI | Real | MNJI3 | MNJI3 | Senior 3 | AUDIT | 18 |  | Audit IL | [10 empty] | 60%
NJI | Real | MNJI4 | MNJI4 | Senior 3 | AUDIT | 18 |  | Audit IL | [5 empty] | 100%
NJI | Real | MNJI5 | MNJI5 | Senior 3 | AUDIT | 18 |  | Audit IL | [9 empty] | 60% | 40%
MJ | Real | MJ1 | MJ1 | Assistant Manager 2 | AUDIT | 22 |  | Audit ERK |  |  | 100% | 100% |  |  |  | 100%
MJ | Real | MJ2 | MJ2 | Assistant Manager 2 | AUDIT | 22 |  | Audit ERK | 100% | 100%
MJ | Real | MJ3 | MJ3 | Assistant Manager 2 | AUDIT | 22 |  | Audit ERK |  |  |  |  | 100% | 100% |  |  | 20%
MJ | Real | MJ4 | MJ4 | Assistant Manager 2 | AUDIT | 22 |  | Audit ERK | [6 empty] | 100%
KEJ | Real | MKEJ1 | MKEJ1 | Junior 2 | AUDIT | 17 |  | Audit IL | [7 empty] | 100%
KEJ | Real | MKEJ2 | MKEJ2 | Junior 2 | AUDIT | 17 |  | Audit IL | [11 empty] | 80%
KEJ | Real | MKEJ3 | MKEJ3 | Junior 2 | AUDIT | 17 |  | Audit IL | 100%
KEJ | Real | MKEJ4 | MKEJ4 | Junior 2 | AUDIT | 17 |  | Audit IL | [5 empty] | 40% | 100%
KEJ | Real | MKEJ5 | MKEJ5 | Junior 2 | AUDIT | 17 |  | Audit IL | [8 empty] | 60% | 40%
KEJ | Real | MKEJ6 | MKEJ6 | Junior 2 | AUDIT | 17 |  | Audit IL |  |  |  | 100% | 100% | 40% | [5 empty] | 20%
KEJ | Real | MKEJ7 | MKEJ7 | Junior 2 | AUDIT | 17 |  | Audit IL | [9 empty] | 40% | 100%
MPHA | Real | MMPHA001 | MMPHA001 | Partner | AUDIT | 7.63 |  | Audit MHZ |  | 20% | 20% |  | 20% |  | 10% |  |  | 10% |  | 10% | 17%
MPHA | Real | MMPHA002 | MMPHA002 | Partner | AUDIT | 7.63 |  | Audit MHZ |  |  | 20% | 10%
MPHA | Real | MMPHA003 | MMPHA003 | Partner | AUDIT | 7.63 |  | Audit MHZ | [11 empty] | 10%
MPHA | Real | MMPHA004 | MMPHA004 | Partner | AUDIT | 7.63 |  | Audit MHZ | 30% |  |  |  |  | 5% |  | 10%
MPHA | Real | MMPHA005 | MMPHA005 | Partner | AUDIT | 7.63 |  | Audit MHZ | [5 empty] | 15% | 10% | 10%
MPHA | Real | MMPHA006 | MMPHA006 | Partner | AUDIT | 7.63 |  | Audit MHZ | [10 empty] | 10% | 10%
MPHA | Real | MMPHA007 | MMPHA007 | Partner | AUDIT | 7.63 |  | Audit MHZ | [10 empty] | 10%
MPHA | Real | MMPHA008 | MMPHA008 | Partner | AUDIT | 7.63 |  | Audit MHZ | [10 empty] | 10%
MPHA | Real | MMPHA009 | MMPHA009 | Partner | AUDIT | 7.63 |  | Audit MHZ |  |  |  | 20% |  |  | 10% |  | 10%
MPHA | Real | MMPHA0010 | MMPHA0010 | Partner | AUDIT | 7.63 |  | Audit MHZ | 10% |  | 20% | 10%
MPHA | Real | MMPHA0011 | MMPHA0011 | Partner | AUDIT | 7.63 |  | Audit MHZ | 20% | 40% | 20% | 10% | 18% | 20% | 23% | 30% | 20% | 30% | 40% | 40% | 33%
MPHA | Real | MMPHA0012 | MMPHA0012 | Partner | AUDIT | 7.63 |  | Audit MHZ |  | 10% |  | 10% | 13% | 8% | 8% | 8% | 10% |  |  | 10% | 17%
MPHA | Real | MMPHA0013 | MMPHA0013 | Partner | AUDIT | 7.63 |  | Audit MHZ | [10 empty] | 10%
MPHA | Real | MMPHA0014 | MMPHA0014 | Partner | AUDIT | 7.63 |  | Audit MHZ | [7 empty] | 10%
MPHA | Real | MMPHA0015 | MMPHA0015 | Partner | AUDIT | 7.63 |  | Audit MHZ |  |  |  |  | 10%
MPHA | Real | MMPHA0016 | MMPHA0016 | Partner | AUDIT | 7.63 |  | Audit MHZ | [7 empty] | 10%
MPHA | Real | MMPHA0017 | MMPHA0017 | Partner | AUDIT | 7.63 |  | Audit MHZ | [7 empty] | 10% |  |  |  |  | 17%
MPHA | Real | MMPHA0018 | MMPHA0018 | Partner | AUDIT | 7.63 |  | Audit MHZ | 20% |  |  | 10% | [6 empty] | 10% |  | 17%
MPHA | Real | MMPHA0019 | MMPHA0019 | Partner | AUDIT | 7.63 |  | Audit MHZ | [8 empty] | 10%
MPHA | Real | MMPHA0020 | MMPHA0020 | Partner | AUDIT | 7.63 |  | Audit MHZ |  | 20% |  |  | 10% | [6 empty] | 20%
MPHA | Real | MMPHA0021 | MMPHA0021 | Partner | AUDIT | 7.63 |  | Audit MHZ | [8 empty] | 10%
MPHA | Real | MMPHA0023 | MMPHA0023 | Partner | AUDIT | 7.63 |  | Audit MHZ | 10% |  | 10%
MPHA | Real | MMPHA0023 | MMPHA0023 | Partner | AUDIT | 7.63 |  | Audit MHZ | 10% |  | 10%
MPHA | Real | MMPHA0024 | MMPHA0024 | Partner | AUDIT | 7.63 |  | Audit MHZ | [5 empty] | 10% | 10%
MPHA | Real | MMPHA0025 | MMPHA0025 | Partner | AUDIT | 7.63 |  | Audit MHZ | [9 empty] | 5%
MPHA | Real | MMPHA0026 | MMPHA0026 | Partner | AUDIT | 7.63 |  | Audit MHZ | [10 empty] | 5%
MPHA | Real | MMPHA0027 | MMPHA0027 | Partner | AUDIT | 7.63 |  | Audit MHZ | [9 empty] | 10%
MPHA | Real | MMPHA0028 | MMPHA0028 | Partner | AUDIT | 7.63 |  | Audit MHZ | [5 empty] | 8%
MPHA | Real | MMPHA0029 | MMPHA0029 | Partner | AUDIT | 7.63 |  | Audit MHZ |  | 10% |  | 20% | 15% | 20% |  |  |  | 20%
MAH | Real | MMAH1 | MMAH1 | Junior 1 | AUDIT | 6 |  | Audit SM |  |  |  |  | 100% | 100% | 20%
MAH | Real | MMAH2 | MMAH2 | Junior 1 | AUDIT | 6 |  | Audit SM | [12 empty] | 100%
MAH | Real | MMAH3 | MMAH3 | Junior 1 | AUDIT | 6 |  | Audit SM | [9 empty] | 20% |  |  | 33%
MAH | Real | MMAH4 | MMAH4 | Junior 1 | AUDIT | 6 |  | Audit SM | [6 empty] | 80% | 100% | 60%
MAH | Real | MMAH5 | MMAH5 | Junior 1 | AUDIT | 6 |  | Audit SM | 100% | 100%
MAH | Real | MMAH6 | MMAH6 | Junior 1 | AUDIT | 6 |  | Audit SM |  |  | 100% | 100%
MAH | Real | MMAH7 | MMAH7 | Junior 1 | AUDIT | 6 |  | Audit SM | [10 empty] | 100% | 100%
ISA | Real | ISA1 | ISA1 | Junior 2 | AUDIT | 2 |  | Audit MHZ |  | 100% | 100% |  | 100% | 60% | 60% | 100% | 40% | 100% | 80% | 100%
ISA | Real | ISA2 | ISA2 | Junior 2 | AUDIT | 2 |  | Audit MHZ |  |  |  | 100% |  | 40% | 40% |  | 20%
ISA | Real | ISA3 | ISA3 | Junior 2 | AUDIT | 2 |  | Audit MHZ | [10 empty] | 20% |  | 100%
ISA | Real | ISA4 | ISA4 | Junior 2 | AUDIT | 2 |  | Audit MHZ | 100%
MDH | Real | MMDH1 | MMDH1 | Senior Manager 4 | AUDIT | 4 |  | Audit MAB | [7 empty] | 20% | 40%
MDH | Real | MMDH2 | MMDH2 | Senior Manager 4 | AUDIT | 4 |  | Audit MAB | [6 empty] | 20%
MDH | Real | MMDH3 | MMDH3 | Senior Manager 4 | AUDIT | 4 |  | Audit MAB |  |  |  | 60% | 20% |  |  |  |  | 20%
MDH | Real | MMDH4 | MMDH4 | Senior Manager 4 | AUDIT | 4 |  | Audit MAB | [5 empty] | 20%
MDH | Real | MMDH5 | MMDH5 | Senior Manager 4 | AUDIT | 4 |  | Audit MAB | 80% | 80% | 40% |  | 60% | 60% | 20% | 40% | 20% | 40% | 20% | 20% | 33%
MDH | Real | MMDH6 | MMDH6 | Senior Manager 4 | AUDIT | 4 |  | Audit MAB | [10 empty] | 80% | 80% | 67%
MDH | Real | MMDH7 | MMDH7 | Senior Manager 4 | AUDIT | 4 |  | Audit MAB |  |  | 40%
MDH | Real | MMDH8 | MMDH8 | Senior Manager 4 | AUDIT | 4 |  | Audit MAB |  |  |  |  | 20% | 20% | 40%
MDH | Real | MMDH9 | MMDH9 | Senior Manager 4 | AUDIT | 4 |  | Audit MAB |  |  |  | 40% |  |  |  | 40%
MDH | Real | MMDH11 | MMDH11 | Senior Manager 4 | AUDIT | 4 |  | Audit MAB | [9 empty] | 20%
MDH | Real | MMDH10 | MMDH10 | Senior Manager 4 | AUDIT | 4 |  | Audit MAB | 20% | 20% | 20%
HAR | Real | HAR1 | HAR1 | Junior 1 | AUDIT | 2 |  | Audit MHZ | [5 empty] | 100%
HAR | Real | HAR2 | HAR2 | Junior 1 | AUDIT | 2 |  | Audit MHZ | [10 empty] | 20%
HAR | Real | HAR3 | HAR3 | Junior 1 | AUDIT | 2 |  | Audit MHZ |  |  | 100% | 100% | 100%
HAR | Real | HAR4 | HAR4 | Junior 1 | AUDIT | 2 |  | Audit MHZ | 100% | 100%
HAR | Real | HAR5 | HAR5 | Junior 1 | AUDIT | 2 |  | Audit MHZ | [10 empty] | 80% | 100% | 200%
HAR | Real | HAR6 | HAR6 | Junior 1 | AUDIT | 2 |  | Audit MHZ | [6 empty] | 100% | 100% | 60% | 100%
FHD | Real | MFHD1 | MFHD1 | Junior 2 | AUDIT | 2 |  | Audit SM | 100% | 100%
FHD | Real | MFHD2 | MFHD2 | Junior 2 | AUDIT | 2 |  | Audit SM | [7 empty] | 100% | 60% | 100% | 100% | 100% | 100%
FHD | Real | MFHD3 | MFHD3 | Junior 2 | AUDIT | 2 |  | Audit SM | [5 empty] | 100% | 100%
FHD | Real | MFHD4 | MFHD4 | Junior 2 | AUDIT | 2 |  | Audit SM |  | 100% | 100% | 100%
FHD | Real | MFHD5 | MFHD5 | Junior 2 | AUDIT | 2 |  | Audit SM |  |  |  |  | 100%
BQM | Real | MBQM1 | MBQM1 | Senior 1 | AUDIT | 0 |  | Audit KB |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100%
BQM | Real | MBQM2 | MBQM2 | Senior 1 | AUDIT | 0 |  | Audit KB | 100% | 100%
BQM | Real | MBQM3 | MBQM3 | Senior 1 | AUDIT | 0 |  | Audit KB | [9 empty] | 100% | 100%
BQM | Real | MBQM4 | MBQM4 | Senior 1 | AUDIT | 0 |  | Audit KB | [11 empty] | 100% | 100%
HGD | Real | MHGD1 | MHGD1 | Manager 1 | AUDIT | 2 |  | Audit IL |  |  |  |  | 60% | 20%
HGD | Real | MHGD2 | MHGD2 | Manager 1 | AUDIT | 2 |  | Audit IL | [7 empty] | 100%
HGD | Real | MHGD3 | MHGD3 | Manager 1 | AUDIT | 2 |  | Audit IL | [8 empty] | 60%
HGD | Real | MHGD4 | MHGD4 | Manager 1 | AUDIT | 2 |  | Audit IL | [12 empty] | 100%
HGD | Real | MHGD5 | MHGD5 | Manager 1 | AUDIT | 2 |  | Audit IL |  |  |  |  | 40%
HGD | Real | MHGD6 | MHGD6 | Manager 1 | AUDIT | 2 |  | Audit IL | [9 empty] | 20% | 100% | 20%
HGD | Real | MHGD7 | MHGD7 | Manager 1 | AUDIT | 2 |  | Audit IL | 100% | 100% | 100% | 100%
HGD | Real | MHGD8 | MHGD8 | Manager 1 | AUDIT | 2 |  | Audit IL | [5 empty] | 80% | 100% |  |  | 80%
HGD | Real | MHGD9 | MHGD9 | Manager 1 | AUDIT | 2 |  | Audit IL | [11 empty] | 80%
MG | Real | MMG1 | MMG1 | Senior 1 | AUDIT | 22 |  | Audit IL | [7 empty] | 100% | 100% | 60% | 60%
MG | Real | MMG2 | MMG2 | Senior 1 | AUDIT | 22 |  | Audit IL | [10 empty] | 40% | 100% | 100%
MG | Real | MMG3 | MMG3 | Senior 1 | AUDIT | 22 |  | Audit IL | 100% | 100% | 100%
ROS | Real | MROS1 | MROS1 | Senior 2 | AUDIT | 21 |  | Audit KB |  | 100% | 100% | 100% | 100% | 100% | 100%
ROS | Real | MROS2 | MROS2 | Senior 2 | AUDIT | 21 |  | Audit KB | 100% | [8 empty] | 40% | 100%
EG | Real | MEG1 | MEG1 | Junior 1 | AUDIT | 4 |  | Audit SM | 100% | 100% | 100% | 100% | 100%
EG | Real | MEG2 | MEG2 | Junior 1 | AUDIT | 4 |  | Audit SM | [6 empty] | 100% | 100%
EG | Real | MEG3 | MEG3 | Junior 1 | AUDIT | 4 |  | Audit SM | [8 empty] | 60% | 100%
EG | Real | MEG4 | MEG4 | Junior 1 | AUDIT | 4 |  | Audit SM | [5 empty] | 100% |  |  | 20%
EG | Real | MEG5 | MEG5 | Junior 1 | AUDIT | 4 |  | Audit SM | [10 empty] | 100% | 100%
AGH | Real | MAGH2 | MAGH2 | Junior 2 | AUDIT | 9 |  | Audit SM | 100% | 60%
AGH | Real | MAGH3 | MAGH3 | Junior 2 | AUDIT | 9 |  | Audit SM |  |  |  |  | 100% | 100% | 100%
AGH | Real | MAGH4 | MAGH4 | Junior 2 | AUDIT | 9 |  | Audit SM | [11 empty] | 100% | 100%
AGH | Real | MAGH5 | MAGH5 | Junior 2 | AUDIT | 9 |  | Audit SM |  |  | 100% | 100%
AGH | Real | MAGH1 | MAGH1 | Junior 2 | AUDIT | 9 |  | Audit SM | [8 empty] | 60% | 140% | 100%
EMR | Real | EMR1 | EMR1 | Director 1 | AUDIT | 25 |  | Audit MHZ |  |  |  | 100%
EMR | Real | EMR2 | EMR2 | Director 1 | AUDIT | 25 |  | Audit MHZ |  |  |  |  | 100%
EMR | Real | EMR3 | EMR3 | Director 1 | AUDIT | 25 |  | Audit MHZ | 100% | 100% |  |  |  | 100%
EMR | Real | EMR4 | EMR4 | Director 1 | AUDIT | 25 |  | Audit MHZ | [7 empty] | 100% |  |  | 100%
EMR | Real | EMR5 | EMR5 | Director 1 | AUDIT | 25 |  | Audit MHZ | [11 empty] | 60%
ANS | Real | MANS1 | MANS1 | Senior Manager 3 | AUDIT | 45 |  | Audit MHZ | [6 empty] | 100%
ANS | Real | MANS2 | MANS2 | Senior Manager 3 | AUDIT | 45 |  | Audit MHZ | [9 empty] | 100%
ANS | Real | MANS3 | MANS3 | Senior Manager 3 | AUDIT | 45 |  | Audit MHZ |  | 100%
ANS | Real | MANS4 | MANS4 | Senior Manager 3 | AUDIT | 45 |  | Audit MHZ | [12 empty] | 100%
FFK | Real | MFFK1 | MFFK1 | Junior 1 | AUDIT | 10 |  | Audit SM |  |  |  |  | 100% | 100% | 100%
FFK | Real | MFFK2 | MFFK2 | Junior 1 | AUDIT | 10 |  | Audit SM | [8 empty] | 60% | 100%
FFK | Real | MFFK3 | MFFK3 | Junior 1 | AUDIT | 10 |  | Audit SM | [8 empty] | 20%
FFK | Real | MFFK4 | MFFK4 | Junior 1 | AUDIT | 10 |  | Audit SM | [7 empty] | 100%
FFK | Real | MFFK5 | MFFK5 | Junior 1 | AUDIT | 10 |  | Audit SM | [8 empty] | 40%
FFK | Real | MFFK6 | MFFK6 | Junior 1 | AUDIT | 10 |  | Audit SM |  | 100% | 100% | 100%
FFK | Real | MFFK7 | MFFK7 | Junior 1 | AUDIT | 10 |  | Audit SM | [10 empty] | 100% | 100%
ALS | Real | MALS1 | MALS1 | Senior Manager 2 | AUDIT | 14 |  | Audit IL | 50% | 42% | 30% |  |  | 40%
ALS | Real | MALS2 | MALS2 | Senior Manager 2 | AUDIT | 14 |  | Audit IL | 20%
ALS | Real | MALS3 | MALS3 | Senior Manager 2 | AUDIT | 14 |  | Audit IL | 20% | 40% | [7 empty] | 60%
ALS | Real | MALS4 | MALS4 | Senior Manager 2 | AUDIT | 14 |  | Audit IL | 10%
ALS | Real | MALS5 | MALS5 | Senior Manager 2 | AUDIT | 14 |  | Audit IL | [8 empty] | 30% | 20% | 10%
ALS | Real | MALS6 | MALS6 | Senior Manager 2 | AUDIT | 14 |  | Audit IL |  |  |  |  | 20% | 20% | 20% | 30% | 18% | 20%
ALS | Real | MALS7 | MALS7 | Senior Manager 2 | AUDIT | 14 |  | Audit IL |  |  |  |  | 20% | 20% | 20% | 20%
ALS | Real | MALS8 | MALS8 | Senior Manager 2 | AUDIT | 14 |  | Audit IL | [8 empty] | 12% |  | 20%
ALS | Real | MALS9 | MALS9 | Senior Manager 2 | AUDIT | 14 |  | Audit IL |  |  |  | 30% | 20% | 20% |  |  |  |  | 40%
ALS | Real | MALS10 | MALS10 | Senior Manager 2 | AUDIT | 14 |  | Audit IL |  |  | 30% | 30% | 20% |  | 20%
ALS | Real | MALS11 | MALS11 | Senior Manager 2 | AUDIT | 14 |  | Audit IL |  | 18% |  | 20% | 20% |  | 20%
ALS | Real | MALS12 | MALS12 | Senior Manager 2 | AUDIT | 14 |  | Audit IL |  |  | 20% | 20% |  |  |  | 20% |  |  | 20%
FEK | Real | MFEK1 | MFEK1 | Junior 2 | AUDIT | 22 |  | Audit ERK |  |  |  |  | 100%
FEK | Real | MFEK2 | MFEK2 | Junior 2 | AUDIT | 22 |  | Audit ERK |  |  | 100% | 100% |  |  |  |  | 20%
FEK | Real | MFEK3 | MFEK3 | Junior 2 | AUDIT | 22 |  | Audit ERK | [5 empty] | 100%
FEK | Real | MFEK4 | MFEK4 | Junior 2 | AUDIT | 22 |  | Audit ERK | 100% | 100%
FEK | Real | MFEK5 | MFEK5 | Junior 2 | AUDIT | 22 |  | Audit ERK | [7 empty] | 100%
FEK | Real | MFEK6 | MFEK6 | Junior 2 | AUDIT | 22 |  | Audit ERK | [6 empty] | 100%
MWA | Real | MWA1 | MWA1 | Assistant Manager 1 | AUDIT | 34 |  | Audit SM | 100% | 100%
MWA | Real | MWA2 | MWA2 | Assistant Manager 1 | AUDIT | 34 |  | Audit SM |  |  |  |  | 100% | 100% | 100%
MWA | Real | MWA3 | MWA3 | Assistant Manager 1 | AUDIT | 34 |  | Audit SM |  |  | 60%
MWA | Real | MWA4 | MWA4 | Assistant Manager 1 | AUDIT | 34 |  | Audit SM | [12 empty] | 33%
MIK | Real | MMIK1 | MMIK1 | Manager 3 | AUDIT | 38 |  | Audit MHZ |  |  | 100% | 100%
MIK | Real | MMIK2 | MMIK2 | Manager 3 | AUDIT | 38 |  | Audit MHZ | 60%
MIK | Real | MMIK3 | MMIK3 | Manager 3 | AUDIT | 38 |  | Audit MHZ |  | 100%
MIK | Real | MMIK4 | MMIK4 | Manager 3 | AUDIT | 38 |  | Audit MHZ | 40%
MIK | Real | MMIK5 | MMIK5 | Manager 3 | AUDIT | 38 |  | Audit MHZ |  |  |  |  | 100%
ECR | Real | MECR1 | MECR1 | Junior 1 | AUDIT | 5 |  | Audit MAB |  |  |  | 20%
ECR | Real | MECR2 | MECR2 | Junior 1 | AUDIT | 5 |  | Audit MAB | [10 empty] | 100% | 100% | 100%
ECR | Real | MECR3 | MECR3 | Junior 1 | AUDIT | 5 |  | Audit MAB | [8 empty] | 40% | 80%
ECR | Real | MECR4 | MECR4 | Junior 1 | AUDIT | 5 |  | Audit MAB |  |  |  |  | 100% | 100%
ECR | Real | MECR5 | MECR5 | Junior 1 | AUDIT | 5 |  | Audit MAB | 80% | 100% | 100% | 80% |  |  | 80% | 100% | 20%
HC | Real | MHC1 | MHC1 | Junior 1 | AUDIT | 7 |  | Audit MHZ |  |  | 100% | 100% | 100% | 60% | 60% | 100% | 60% | 100% | 100% | 100% | 100%
HC | Real | MHC2 | MHC2 | Junior 1 | AUDIT | 7 |  | Audit MHZ | [5 empty] | 40% | 40%
HC | Real | MHC3 | MHC3 | Junior 1 | AUDIT | 7 |  | Audit MHZ | 100%
ABS | Real | MABS1 | MABS1 | Senior 3 | AUDIT | 2 |  | Audit MHZ | [5 empty] | 100% | 100% | 100% | 60% | 100%
ABS | Real | MABS2 | MABS2 | Senior 3 | AUDIT | 2 |  | Audit MHZ |  |  |  | 60%
ABS | Real | MABS3 | MABS3 | Senior 3 | AUDIT | 2 |  | Audit MHZ | 100% | 100% | 100% | 40% | 100% | [5 empty] | 100% | 100% | 100%
IB | Real | MIB1 | MIB1 | Assistant Manager 2 | AUDIT | 52 |  | Audit MHZ |  |  |  | 100% | 100%
IB | Real | MIB2 | MIB2 | Assistant Manager 2 | AUDIT | 52 |  | Audit MHZ | 20%
KBG | Real | MKGB1 | MKGB1 | Partner | AUDIT | 34 |  | Audit KB |  | 40%
KBG | Real | MKGB2 | MKGB2 | Partner | AUDIT | 34 |  | Audit KB | [11 empty] | 60%
KBG | Real | MKGB3 | MKGB3 | Partner | AUDIT | 34 |  | Audit KB | [8 empty] | 20%
KBG | Real | MKGB4 | MKGB4 | Partner | AUDIT | 34 |  | Audit KB | [5 empty] | 40%
KBG | Real | MKGB5 | MKGB5 | Partner | AUDIT | 34 |  | Audit KB | 60%
KBG | Real | MKGB6 | MKGB6 | Partner | AUDIT | 34 |  | Audit KB | [6 empty] | 40%
KBG | Real | MKGB7 | MKGB7 | Partner | AUDIT | 34 |  | Audit KB | 40%
KBG | Real | MKGB8 | MKGB8 | Partner | AUDIT | 34 |  | Audit KB |  |  |  | 40% | [5 empty] | 40%
KBG | Real | MKGB9 | MKGB9 | Partner | AUDIT | 34 |  | Audit KB |  |  |  |  | 40%
KBG | Real | MKGB10 | MKGB10 | Partner | AUDIT | 34 |  | Audit KB | [7 empty] | 40%
KBG | Real | MKGB11 | MKGB11 | Partner | AUDIT | 34 |  | Audit KB |  |  |  | 40%
KBG | Real | MKGB12 | MKGB12 | Partner | AUDIT | 34 |  | Audit KB |  | 40%
KBG | Real | MKGB13 | MKGB13 | Partner | AUDIT | 34 |  | Audit KB |  |  | 40%
HBG | Real | MHBG1 | MHBG1 | Senior Manager 1 | AUDIT | 54 |  | Audit KB |  |  | 60%
HBG | Real | MHBG2 | MHBG2 | Senior Manager 1 | AUDIT | 54 |  | Audit KB | 60%
HBG | Real | MHBG3 | MHBG3 | Senior Manager 1 | AUDIT | 54 |  | Audit KB |  | 60%
BMA | Real | MBMA1 | MBMA1 | Senior 2 | AUDIT | 3 |  | Audit MHZ | [12 empty] | 100%
BMA | Real | MBMA2 | MBMA2 | Senior 2 | AUDIT | 3 |  | Audit MHZ | [6 empty] | 100% | 80% | 40%
BMA | Real | MBMA3 | MBMA3 | Senior 2 | AUDIT | 3 |  | Audit MHZ |  | 100% |  | 100% | 100% | 100% |  |  |  | 40%
BMA | Real | MBMA4 | MBMA4 | Senior 2 | AUDIT | 3 |  | Audit MHZ |  |  | 100% |  |  |  |  | 20% |  | 40%
BMA | Real | MBMA5 | MBMA5 | Senior 2 | AUDIT | 3 |  | Audit MHZ | 100%
BMA | Real | MBMA6 | MBMA6 | Senior 2 | AUDIT | 3 |  | Audit MHZ | [10 empty] | 100% | 100%
BMA | Real | MBMA7 | MBMA7 | Senior 2 | AUDIT | 3 |  | Audit MHZ | [8 empty] | 20%
BGZ | Real | MBGZ1 | MBGZ1 | Senior 1 | AUDIT | 5 |  | Audit SM |  |  |  | 100% | 100% | 100%
BGZ | Real | MBGZ2 | MBGZ2 | Senior 1 | AUDIT | 5 |  | Audit SM | [6 empty] | 20%
BGZ | Real | MBGZ3 | MBGZ3 | Senior 1 | AUDIT | 5 |  | Audit SM | [10 empty] | 100% | 100%
BGZ | Real | MBGZ4 | MBGZ4 | Senior 1 | AUDIT | 5 |  | Audit SM | [9 empty] | 60%
BGZ | Real | MBGZ5 | MBGZ5 | Senior 1 | AUDIT | 5 |  | Audit SM | [6 empty] | 80% | 100% | 60% | 60%
BGZ | Real | MBGZ6 | MBGZ6 | Senior 1 | AUDIT | 5 |  | Audit SM | 100% | 100% | 100% | 100%
BSO | Real | MBSO1 | MBSO1 | Senior 3 | AUDIT | 3 |  | Audit MHZ |  |  |  | 100% | 100% | 100% | 100% | 100% | 60% | 80% | 100% | 100% | 100%
BSO | Real | MBSO2 | MBSO2 | Senior 3 | AUDIT | 3 |  | Audit MHZ | 100% | 100% | 100%
SID | Real | SID1 | SID1 | Senior 1 | AUDIT | 20 |  | Audit MAB | [7 empty] | 20%
SID | Real | SID2 | SID2 | Senior 1 | AUDIT | 20 |  | Audit MAB |  |  | 40%
SID | Real | SID3 | SID3 | Senior 1 | AUDIT | 20 |  | Audit MAB |  |  |  | 20% |  |  | 40% |  |  | 20%
SID | Real | SID4 | SID4 | Senior 1 | AUDIT | 20 |  | Audit MAB |  |  |  |  | 60% | 60% |  |  | 20%
SID | Real | SID5 | SID5 | Senior 1 | AUDIT | 20 |  | Audit MAB |  |  |  | 80%
SID | Real | SID6 | SID6 | Senior 1 | AUDIT | 20 |  | Audit MAB | [8 empty] | 40% | 60%
SID | Real | SID7 | SID7 | Senior 1 | AUDIT | 20 |  | Audit MAB |  |  |  |  | 40% | 40%
SID | Real | SID8 | SID8 | Senior 1 | AUDIT | 20 |  | Audit MAB | [7 empty] | 80%
SID | Real | SID9 | SID9 | Senior 1 | AUDIT | 20 |  | Audit MAB | 100% | 100% |  |  |  |  | 40%
DB | Real | DB1 | DB1 | Senior Manager 1 | AUDIT | 24 |  | Audit ERK | 50% | 30% | 90% | 90% | 90% | 50% | 90% | 70% | 14%
DB | Real | DB2 | DB2 | Senior Manager 1 | AUDIT | 24 |  | Audit ERK | 40% | 15%
DB | Real | DB3 | DB3 | Senior Manager 1 | AUDIT | 24 |  | Audit ERK | 5% | 50% | 5% | 5% | 5% | 5% | 5% | 15% | 3%
DB | Real | DB4 | DB4 | Senior Manager 1 | AUDIT | 24 |  | Audit ERK | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 15% | 3%
BBB | Real | MBBB1 | MBBB1 | Junior 1 | AUDIT | 2 |  | Audit MHZ | [5 empty] | 100% | 100% | 100% | 60% | 100%
BBB | Real | MBBB2 | MBBB2 | Junior 1 | AUDIT | 2 |  | Audit MHZ | [10 empty] | 100% | 100% | 100%
BBB | Real | MBBB3 | MBBB3 | Junior 1 | AUDIT | 2 |  | Audit MHZ | 100% |  |  | 100%
BBB | Real | MBBB4 | MBBB4 | Junior 1 | AUDIT | 2 |  | Audit MHZ |  | 100% | 100% |  | 100%
MBT | Real | MMBT1 | MMBT1 | Junior 2 | AUDIT | 2 |  | Audit SM | 100% | 100%
MBT | Real | MMBT2 | MMBT2 | Junior 2 | AUDIT | 2 |  | Audit SM |  |  | 100% | 100%
MBT | Real | MMBT3 | MMBT3 | Junior 2 | AUDIT | 2 |  | Audit SM | [7 empty] | 100% | 60% | 100% | 100%
MBT | Real | MMBT4 | MMBT4 | Junior 2 | AUDIT | 2 |  | Audit SM | [11 empty] | 100% | 100%
MBT | Real | MMBT5 | MMBT5 | Junior 2 | AUDIT | 2 |  | Audit SM | [9 empty] | 40%
MBT | Real | MMBT6 | MMBT6 | Junior 2 | AUDIT | 2 |  | Audit SM |  |  |  |  | 100% | 60%
MBT | Real | MMBT7 | MMBT7 | Junior 2 | AUDIT | 2 |  | Audit SM | [5 empty] | 40% | 100%
MBS | Real | MBS1 | MBS1 | Junior 2 | AUDIT | 2 |  | Audit MHZ | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 60% | 100% | 100% | 100% | 100%
MSS | Real | MMSS1 | MMSS1 | Manager 3 | AUDIT | 4 |  | Audit IL |  |  | 10% |  |  |  | 10% | 10% |  |  | 20%
MSS | Real | MMSS2 | MMSS2 | Manager 3 | AUDIT | 4 |  | Audit IL |  | 40% | 20% | 20% | 30% | 60% | 40%
MSS | Real | MMSS3 | MMSS3 | Manager 3 | AUDIT | 4 |  | Audit IL | 60% |  | 20% | 20% |  | 20% |  | 10%
MSS | Real | MMSS4 | MMSS4 | Manager 3 | AUDIT | 4 |  | Audit IL | [5 empty] | 20% |  | 10% |  | 40% | 30% | 40% | 33%
MSS | Real | MMSS5 | MMSS5 | Manager 3 | AUDIT | 4 |  | Audit IL |  | 20%
MSS | Real | MMSS6 | MMSS6 | Manager 3 | AUDIT | 4 |  | Audit IL | 20% |  |  | 40% | 10% |  |  | 20% |  | 20% | 10% | 20% | 17%
MSS | Real | MMSS7 | MMSS7 | Manager 3 | AUDIT | 4 |  | Audit IL | [8 empty] | 40%
MSS | Real | MMSS8 | MMSS8 | Manager 3 | AUDIT | 4 |  | Audit IL | [10 empty] | 10%
MSS | Real | MMSS9 | MMSS9 | Manager 3 | AUDIT | 4 |  | Audit IL | 20% |  |  |  | 40% |  | 20% | 10% |  | 20% | 20% | 10%
MSS | Real | MMSS10 | MMSS10 | Manager 3 | AUDIT | 4 |  | Audit IL |  | 40% | 40% |  | 20% |  |  | 10% |  | 20% |  | 10%
MSS | Real | MMSS11 | MMSS11 | Manager 3 | AUDIT | 4 |  | Audit IL | [7 empty] | 10% |  |  |  | 10%
MSS | Real | MMSS12 | MMSS12 | Manager 3 | AUDIT | 4 |  | Audit IL |  |  |  | 20% |  |  |  | 10% | 10% |  |  |  | 17%
MSS | Real | MMSS13 | MMSS13 | Manager 3 | AUDIT | 4 |  | Audit IL |  |  | 10% |  |  |  | 10% | 10% | 10% |  | 10% | 10%
NDB | Real | MNDB1 | MNDB1 | Junior 1 | AUDIT | 3 |  | Audit MAB | [7 empty] | 20% | 60% | 80%
NDB | Real | MNDB2 | MNDB2 | Junior 1 | AUDIT | 3 |  | Audit MAB | 20% | 40% | 60% | 20%
NDB | Real | MNDB3 | MNDB3 | Junior 1 | AUDIT | 3 |  | Audit MAB | 20% | 20% |  | 60% | 100% | 100% | 100% | 40%
NDB | Real | MNDB4 | MNDB4 | Junior 1 | AUDIT | 3 |  | Audit MAB | [10 empty] | 100% | 100% | 100%
NDB | Real | MNDB5 | MNDB5 | Junior 1 | AUDIT | 3 |  | Audit MAB | 20% | 20% | 20% | 20% |  |  |  | 40%
NDB | Real | MNDB6 | MNDB6 | Junior 1 | AUDIT | 3 |  | Audit MAB | 40% | 20% | 20%
BBL | Real | BBL1 | BBL1 | Junior 1 | AUDIT | 2 |  | Audit MHZ | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 60% | 100% | 100% | 100% | 100%
MOL | Real | MMOL1 | MMOL1 | Junior 2 | AUDIT | 12 |  | Audit SM | 100% | 100% | 100% | 100%
MOL | Real | MMOL2 | MMOL2 | Junior 2 | AUDIT | 12 |  | Audit SM |  |  |  |  | 100% | 20%
MOL | Real | MMOL3 | MMOL3 | Junior 2 | AUDIT | 12 |  | Audit SM | [5 empty] | 40% | 40%
MOL | Real | MMOL4 | MMOL4 | Junior 2 | AUDIT | 12 |  | Audit SM | [12 empty] | 100%
MOL | Real | MMOL5 | MMOL5 | Junior 2 | AUDIT | 12 |  | Audit SM | [8 empty] | 60% | 100% | 100% | 100%
MBH | Real | MBH1 | MBH1 | Senior 3 | AUDIT | 2 |  | Audit MHZ | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 60% | 100% | 100% | 100% | 100%
GBH | Real | MGBH1 | MGBH1 | Junior 2 | AUDIT | 2 |  | Audit MHZ | 60% | 50% | 50%
GBH | Real | MGBH2 | MGBH2 | Junior 2 | AUDIT | 2 |  | Audit MHZ | 40% | 50% | 50%
GBH | Real | MGBH3 | MGBH3 | Junior 2 | AUDIT | 2 |  | Audit MHZ |  |  |  | 100% | 100% | 100% | 100% | 100% | 60% | 100% | 100% | 100% | 100%
HBH | Real | MHBH1 | MHBH1 | Junior 2 | AUDIT | 10 |  | Audit KB | 100%
HBH | Real | MHBH2 | MHBH2 | Junior 2 | AUDIT | 10 |  | Audit KB |  |  |  | 100% | [6 empty] | 100%
HBH | Real | MHBH3 | MHBH3 | Junior 2 | AUDIT | 10 |  | Audit KB |  |  |  |  | 100% |  |  |  |  | 100%
HBH | Real | MHBH4 | MHBH4 | Junior 2 | AUDIT | 10 |  | Audit KB | [7 empty] | 100%
HBH | Real | MHBH5 | MHBH5 | Junior 2 | AUDIT | 10 |  | Audit KB | [5 empty] | 100% |  |  | 100%
HBH | Real | MHBH6 | MHBH6 | Junior 2 | AUDIT | 10 |  | Audit KB | [11 empty] | 100% | 100%
HBH | Real | MHBH7 | MHBH7 | Junior 2 | AUDIT | 10 |  | Audit KB | [6 empty] | 100%
DBH | Real | DBH1 | DBH1 | Senior 1 | AUDIT | 0 |  | Audit IL | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
MIA | Real | MMIA1 | MMIA1 | Manager 3 | AUDIT | 35.17 |  | Audit IL | [7 empty] | 100%
MIA | Real | MMIA2 | MMIA2 | Manager 3 | AUDIT | 35.17 |  | Audit IL |  |  |  |  | 10%
MIA | Real | MMIA3 | MMIA3 | Manager 3 | AUDIT | 35.17 |  | Audit IL | [10 empty] | 60%
MIA | Real | MMIA4 | MMIA4 | Manager 3 | AUDIT | 35.17 |  | Audit IL |  |  | 20%
MIA | Real | MMIA5 | MMIA5 | Manager 3 | AUDIT | 35.17 |  | Audit IL |  |  |  | 20%
MIA | Real | MMIA6 | MMIA6 | Manager 3 | AUDIT | 35.17 |  | Audit IL |  |  |  | 40%
MIA | Real | MMIA7 | MMIA7 | Manager 3 | AUDIT | 35.17 |  | Audit IL |  |  |  |  | 7%
MIA | Real | MMIA8 | MMIA8 | Manager 3 | AUDIT | 35.17 |  | Audit IL |  |  | 40%
MIA | Real | MMIA9 | MMIA9 | Manager 3 | AUDIT | 35.17 |  | Audit IL |  | 100%
MIA | Real | MMIA10 | MMIA10 | Manager 3 | AUDIT | 35.17 |  | Audit IL | 100%
MIA | Real | MMIA11 | MMIA11 | Manager 3 | AUDIT | 35.17 |  | Audit IL | [5 empty] | 40%
MIA | Real | MMIA12 | MMIA12 | Manager 3 | AUDIT | 35.17 |  | Audit IL |  |  |  |  | 20%
HBS | Real | MHBS1 | MHBS1 | Junior 1 | AUDIT | 2 |  | Audit SM | 100% | 100%
HBS | Real | MHBS2 | MHBS2 | Junior 1 | AUDIT | 2 |  | Audit SM |  |  |  |  | 100% | 100% | 100% | 100%
HBS | Real | MHBS3 | MHBS3 | Junior 1 | AUDIT | 2 |  | Audit SM | [8 empty] | 60% | 100% | 100% | 100% | 100%
HBS | Real | MHBS4 | MHBS4 | Junior 1 | AUDIT | 2 |  | Audit SM |  |  | 100% | 100%
IBG | Real | MIBG1 | MIBG1 | Senior 3 | AUDIT | 2 |  | Audit SM | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 60% | 100% | 100% | 100% | 100%
HAB | Real | MHAB1 | MHAB1 | Senior 2 | AUDIT | 3 |  | Audit IL | [12 empty] | 100%
HAB | Real | MHAB2 | MHAB2 | Senior 2 | AUDIT | 3 |  | Audit IL | [7 empty] | 100% | 60%
HAB | Real | MHAB3 | MHAB3 | Senior 2 | AUDIT | 3 |  | Audit IL | [6 empty] | 100%
HAB | Real | MHAB4 | MHAB4 | Senior 2 | AUDIT | 3 |  | Audit IL | [9 empty] | 80% | 100% | 60%
HAB | Real | MHAB5 | MHAB5 | Senior 2 | AUDIT | 3 |  | Audit IL | [11 empty] | 40%
HAB | Real | MHAB6 | MHAB6 | Senior 2 | AUDIT | 3 |  | Audit IL | 100% | 100% | 100% | 100% | 100%
HAB | Real | MHAB7 | MHAB7 | Senior 2 | AUDIT | 3 |  | Audit IL | [5 empty] | 100%
ABD | Real | ABD1 | ABD1 | Junior 1 | AUDIT | 44 |  | Audit IL | 100% | 100%
ABD | Real | ABD2 | ABD2 | Junior 1 | AUDIT | 44 |  | Audit IL |  |  |  | 40%
ABD | Real | ABD3 | ABD3 | Junior 1 | AUDIT | 44 |  | Audit IL |  |  | 20%
ABD | Real | ABD4 | ABD4 | Junior 1 | AUDIT | 44 |  | Audit IL |  |  | 80% | 40%
MA | Real | MMA1 | MMA1 | Senior 1 | AUDIT | 22 |  | Audit ERK | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 6%
MA | Real | MMA2 | MMA2 | Senior 1 | AUDIT | 22 |  | Audit ERK | 70% | 70% | 70% | 70% | 70% | 70% | 70% | 70% | 14%
KBAM | Real | MKBAM1 | MKBAM1 | Senior 3 | AUDIT | 22 |  | Audit ERK | 70% | 70% | 70% | 70% | 70% | 70% | 70% | 70% | 14%
KBAM | Real | MKBAM2 | MKBAM2 | Senior 3 | AUDIT | 22 |  | Audit ERK | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 4%
KBAM | Real | MKBAM3 | MKBAM3 | Senior 3 | AUDIT | 22 |  | Audit ERK | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 2%
LBA | Real | MLBA1 | MLBA1 | Junior 2 | AUDIT | 5 |  | Audit SM | 100% | 100% |  |  |  | 100%
LBA | Real | MLBA2 | MLBA2 | Junior 2 | AUDIT | 5 |  | Audit SM | [8 empty] | 40%
LBA | Real | MLBA3 | MLBA3 | Junior 2 | AUDIT | 5 |  | Audit SM | [7 empty] | 100% | 20% | 100% | 100% | 100%
LBA | Real | MLBA4 | MLBA4 | Junior 2 | AUDIT | 5 |  | Audit SM | [6 empty] | 100%
LBA | Real | MLBA5 | MLBA5 | Junior 2 | AUDIT | 5 |  | Audit SM |  |  |  | 100% | 100%
LBA | Real | MLBA6 | MLBA6 | Junior 2 | AUDIT | 5 |  | Audit SM |  | 100% | 100%
AIB | Real | MAIB1 | MAIB1 | Junior 1 | AUDIT | 8 |  | Audit KB | 100% | 100%
AIB | Real | MAIB2 | MAIB2 | Junior 1 | AUDIT | 8 |  | Audit KB |  |  | 100% | 100%
AIB | Real | MAIB3 | MAIB3 | Junior 1 | AUDIT | 8 |  | Audit KB |  |  |  |  | 100% | 100% | 100% | 100% | 40% |  | 100% | 100% | 100%
BMLA | Real | MBMLA1 | MBMLA1 | Partner | AUDIT | 11 |  | Audit MAB | 20% | 40%
BMLA | Real | MBMLA2 | MBMLA2 | Partner | AUDIT | 11 |  | Audit MAB | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% |  | 20% | 20% | 20% | 33%
BMLA | Real | MBMLA3 | MBMLA3 | Partner | AUDIT | 11 |  | Audit MAB |  |  |  |  | 20% | 20% | 20% | 20% | 40%
BMLA | Real | MBMLA4 | MBMLA4 | Partner | AUDIT | 11 |  | Audit MAB | 20% |  | 40% | 40% | 40% | 40% | 20% | 60% | 20% | 60% | 80% | 80% | 67%
BMLA | Real | MBMLA5 | MBMLA5 | Partner | AUDIT | 11 |  | Audit MAB | 20% | 20% | 20% | 20%
EB | Real | EB1 | EB1 | Junior 1 | AUDIT | 2 |  | Audit MHZ |  | 100% | 100% | 100% | 100% | 60% | 60% | 100% | 60% | 100% | 80% | 100%
EB | Real | EB2 | EB2 | Junior 1 | AUDIT | 2 |  | Audit MHZ | [5 empty] | 40% | 40%
EB | Real | EB3 | EB3 | Junior 1 | AUDIT | 2 |  | Audit MHZ | [10 empty] | 20% |  | 100%
EB | Real | EB4 | EB4 | Junior 1 | AUDIT | 2 |  | Audit MHZ | 100%
RAY | Real | RAY1 | RAY1 | Senior Manager 2 | AUDIT | 23 |  | Audit IL | [7 empty] | 20%
RAY | Real | RAY2 | RAY2 | Senior Manager 2 | AUDIT | 23 |  | Audit IL | [7 empty] | 40% | 60%
RAY | Real | RAY3 | RAY3 | Senior Manager 2 | AUDIT | 23 |  | Audit IL | [9 empty] | 40%
RAY | Real | RAY4 | RAY4 | Senior Manager 2 | AUDIT | 23 |  | Audit IL | 30% |  |  |  |  | 10%
RAY | Real | RAY5 | RAY5 | Senior Manager 2 | AUDIT | 23 |  | Audit IL | [11 empty] | 40%
RAY | Real | RAY6 | RAY6 | Senior Manager 2 | AUDIT | 23 |  | Audit IL | [9 empty] | 40%
RAY | Real | RAY7 | RAY7 | Senior Manager 2 | AUDIT | 23 |  | Audit IL | [11 empty] | 60%
RAY | Real | RAY8 | RAY8 | Senior Manager 2 | AUDIT | 23 |  | Audit IL |  | 100%
RAY | Real | RAY9 | RAY9 | Senior Manager 2 | AUDIT | 23 |  | Audit IL | 20%
RAY | Real | RAY10 | RAY10 | Senior Manager 2 | AUDIT | 23 |  | Audit IL | 10%
RAY | Real | RAY11 | RAY11 | Senior Manager 2 | AUDIT | 23 |  | Audit IL |  |  |  |  | 90% | 40%
RAY | Real | RAY12 | RAY12 | Senior Manager 2 | AUDIT | 23 |  | Audit IL |  |  | 80% | 80%
RAY | Real | RAY13 | RAY13 | Senior Manager 2 | AUDIT | 23 |  | Audit IL |  |  | 20% | 20%
HBL | Real | HBL1 | HBL1 | Senior 2 | AUDIT | 11 |  | Audit IL | [8 empty] | 60%
HBL | Real | HBL2 | HBL2 | Senior 2 | AUDIT | 11 |  | Audit IL | 100%
HBL | Real | HBL3 | HBL3 | Senior 2 | AUDIT | 11 |  | Audit IL |  |  |  |  | 100% | 100% | 100%
HBL | Real | HBL4 | HBL4 | Senior 2 | AUDIT | 11 |  | Audit IL | [9 empty] | 20%
HBL | Real | HBL5 | HBL5 | Senior 2 | AUDIT | 11 |  | Audit IL | [9 empty] | 60% | 100% | 100%
HBL | Real | HBL6 | HBL6 | Senior 2 | AUDIT | 11 |  | Audit IL |  | 100% | 100% | 100%
IMB | Real | MIMB1 | MIMB1 | Junior 2 | AUDIT | 3 |  | Audit IL | [11 empty] | 100% | 100%
IMB | Real | MIMB2 | MIMB2 | Junior 2 | AUDIT | 3 |  | Audit IL | [7 empty] | 100% | 60%
IMB | Real | MIMB3 | MIMB3 | Junior 2 | AUDIT | 3 |  | Audit IL | [9 empty] | 80% | 40%
IMB | Real | MIMB4 | MIMB4 | Junior 2 | AUDIT | 3 |  | Audit IL | [10 empty] | 60%
IMB | Real | MIMB5 | MIMB5 | Junior 2 | AUDIT | 3 |  | Audit IL | 100% | 100% | 100% | 100% | 100%
IMB | Real | MIMB6 | MIMB6 | Junior 2 | AUDIT | 3 |  | Audit IL | [5 empty] | 100% | 100%
HBA | Real | MHBA1 | MHBA1 | Junior 1 | AUDIT | 4 |  | Audit MAB | [7 empty] | 20% | 60% | 80%
HBA | Real | MHBA2 | MHBA2 | Junior 1 | AUDIT | 4 |  | Audit MAB | 20% | 40% | 60% | 80%
HBA | Real | MHBA3 | MHBA3 | Junior 1 | AUDIT | 4 |  | Audit MAB | 20% | 20% | [5 empty] | 20%
HBA | Real | MHBA4 | MHBA4 | Junior 1 | AUDIT | 4 |  | Audit MAB | [10 empty] | 100% | 100% | 100%
HBA | Real | MHBA5 | MHBA5 | Junior 1 | AUDIT | 4 |  | Audit MAB |  |  |  |  | 100% | 100% | 80%
HBA | Real | MHBA6 | MHBA6 | Junior 1 | AUDIT | 4 |  | Audit MAB | 20% | 20% | 20% | 20% |  |  |  | 60%
HBA | Real | MHBA7 | MHBA7 | Junior 1 | AUDIT | 4 |  | Audit MAB | 40% | 20% | 20%
FRE | Real | MFRE1 | MFRE1 | Senior 2 | AUDIT | 4 |  | Audit SM | [8 empty] | 60%
FRE | Real | MFRE2 | MFRE2 | Senior 2 | AUDIT | 4 |  | Audit SM | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 20%
FRE | Real | MFRE3 | MFRE3 | Senior 2 | AUDIT | 4 |  | Audit SM | [9 empty] | 100% | 100% | 100%
NSA | Real | MNSA1 | MNSA1 | Junior 2 | AUDIT | 2 |  | Audit MHZ | [10 empty] | 100% | 100% | 100%
NSA | Real | MNSA2 | MNSA2 | Junior 2 | AUDIT | 2 |  | Audit MHZ |  |  | 100% | 100% | 100% | 100%
NSA | Real | MNSA3 | MNSA3 | Junior 2 | AUDIT | 2 |  | Audit MHZ | 100% | 100%
NSA | Real | MNSA4 | MNSA4 | Junior 2 | AUDIT | 2 |  | Audit MHZ | [6 empty] | 100% | 100% | 60% | 100%
AA | Real | MAA1 | MAA1 | Senior 2 | AUDIT | 31 |  | Audit IL | 100% | 100% |  |  | 20% |  |  | 40%
AA | Real | MAA2 | MAA2 | Senior 2 | AUDIT | 31 |  | Audit IL |  |  |  |  | 40% | 60%
AA | Real | MAA3 | MAA3 | Senior 2 | AUDIT | 31 |  | Audit IL |  |  | 50% | 50% |  | 40%
AA | Real | MAA4 | MAA4 | Senior 2 | AUDIT | 31 |  | Audit IL |  |  | 50% | 50% | 40%
MRMA | Real | MRMA1 | MRMA1 | Junior 1 | AUDIT | 2 |  | Audit MHZ | [5 empty] | 100% | 100% | 100% | 40% | 100%
MRMA | Real | MRMA2 | MRMA2 | Junior 1 | AUDIT | 2 |  | Audit MHZ | [8 empty] | 20%
MRMA | Real | MRMA3 | MRMA3 | Junior 1 | AUDIT | 2 |  | Audit MHZ |  |  | 100% | 100% | 100%
MRMA | Real | MRMA4 | MRMA4 | Junior 1 | AUDIT | 2 |  | Audit MHZ |  | 100%
MRMA | Real | MRMA5 | MRMA5 | Junior 1 | AUDIT | 2 |  | Audit MHZ | 100%
MRMA | Real | MRMA6 | MRMA6 | Junior 1 | AUDIT | 2 |  | Audit MHZ | [10 empty] | 100% | 100% | 100%
AHM | Real | AHM1 | AHM1 | Junior 2 | AUDIT | 2 |  | Audit SM | [12 empty] | 100%
AHM | Real | AHM2 | AHM2 | Junior 2 | AUDIT | 2 |  | Audit SM |  |  |  |  | 100% | 100% | 100%
AHM | Real | AHM3 | AHM3 | Junior 2 | AUDIT | 2 |  | Audit SM | [7 empty] | 100% | 60% | 100% | 100% | 100%
AHM | Real | AHM4 | AHM4 | Junior 2 | AUDIT | 2 |  | Audit SM | [12 empty] | 100%
AHM | Real | AHM5 | AHM5 | Junior 2 | AUDIT | 2 |  | Audit SM | 100% | 100%
AHM | Real | AHM6 | AHM6 | Junior 2 | AUDIT | 2 |  | Audit SM |  |  | 100% | 100%
ABS | Real | MABS1 | MABS1 | Junior 2 | AUDIT | 2 |  | Audit SM | 100% | 100% |  |  |  | 80%
ABS | Real | MABS2 | MABS2 | Junior 2 | AUDIT | 2 |  | Audit SM | [6 empty] | 100% | 100% | 40%
ABS | Real | MABS3 | MABS3 | Junior 2 | AUDIT | 2 |  | Audit SM |  |  | 100% | 100%
ABS | Real | MABS4 | MABS4 | Junior 2 | AUDIT | 2 |  | Audit SM | [5 empty] | 20% |  |  | 20% |  | 100% | 100% | 100%
ABS | Real | MABS5 | MABS5 | Junior 2 | AUDIT | 2 |  | Audit SM | [9 empty] | 100%
ABS | Simulated | MABS6 | MABS6 | Junior 2 | AUDIT | 2 |  | Audit SM |  |  |  |  | 100% | 100%
IA | Real | MIA1 | MIA1 | Junior 2 | AUDIT | 18 |  | Audit ERK |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100%
IA | Real | MIA2 | MIA2 | Junior 2 | AUDIT | 18 |  | Audit ERK | 100% | 100%
FA | Real | MFA1 | MFA1 | Senior 3 | AUDIT | 38 |  | Audit KB |  |  |  |  | 100% | 100%
FA | Real | MFA2 | MFA2 | Senior 3 | AUDIT | 38 |  | Audit KB |  |  | 100% | 100%
FA | Real | MFA3 | MFA3 | Senior 3 | AUDIT | 38 |  | Audit KB | [6 empty] | 100%
KAM | Real | KAM1 | KAM1 | Manager 3 | AUDIT | 1 |  | Audit KB | [8 empty] | 20% | 100% | 80%
KAM | Real | KAM2 | KAM2 | Manager 3 | AUDIT | 1 |  | Audit KB | 80% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
KAM | Real | KAM3 | KAM3 | Manager 3 | AUDIT | 1 |  | Audit KB | [11 empty] | 80% | 100%
KAM | Real | KAM4 | KAM4 | Manager 3 | AUDIT | 1 |  | Audit KB | 20% | 60% | 40% | 60% | 40% | 40% | 20% | 40% | 40% | 80% | 100% | 100% | 100%
KAM | Real | KAM5 | KAM5 | Manager 3 | AUDIT | 1 |  | Audit KB | [6 empty] | 100%
KAM | Real | KAM6 | KAM6 | Manager 3 | AUDIT | 1 |  | Audit KB | [7 empty] | 80% | 20%
HAB | Real | MHAB1 | MHAB1 | Junior 1 | AUDIT | 23 |  | Audit ERK |  | 50% | 80% | 100% | 100% | 100% | 100% | 100% | 20%
HAB | Real | MHAB2 | MHAB2 | Junior 1 | AUDIT | 23 |  | Audit ERK | 100% | 25%
HAB | Real | MHAB3 | MHAB3 | Junior 1 | AUDIT | 23 |  | Audit ERK |  | 25%